## Sheet1
Priority | Task | Task Details | Goal | Necessary | Resources Needed | Time Allocated | Follow-Up Needed (AH) | Notes | Notes responses from SD
1 | Post to Social Media | - Establish a frequency of posts | - Marketing strategy | YES | - Hootsuite credentials | - SD: 1 day | - Change Hootsuite credentials | -- | Instagram , fb , snapchat , twitter , yelp , linkedin , google plus , pinterest
|  | - Create requirements (ex. 4 PM daily) | - Consistant posts |  | - MH create requirments | - MH: 2 hour (create info and teach SD)
- Establish social medias
| Automate Instagram | - Autolikeing | -Social media popularity | EITHER | - Instagram credentials |  | - Change Instagram credentials | - Can we use bots for Facebook? Or Twitter? | Twitter has very less user engagement. Not useful to spend time bots for twitter . Facebook is a platform where you have to friend people to contact them . Best way to work with facebook is with facebook ads . Facebook ads are expensive though . Would not recommend doing it just now .
|  | - Autocommenting | - Increase "influencers" |  | - Setup test profile | - SD: 1 week (30 hrs) |  | - We're don't have a lot of people commenting/talking to us on social media, but we should get into trend of "liking" posts to increase our followers | Two ways I want to do this : 1 . Like posts from other event managers at weddings , linking posts of profiles of customers , liking posts corresponding to a hashtag .
[5 empty] | - Purchase bots..$7-20 (robolike, gramista, instazood) |  |  | - Will the bots also help us find people to follow in social media? This could increase our followers in return (ex. you scratch my back) | Yes . Can search by hashtag .
Note to MH : Generate list of hashtags which have to be used .
2 | Analyzing Other Profiles | - Researching hashtags | -Social media popularity | YES | - Instagram credentials | - SD/MH: ongoing task | - SD asking how many hours are allowed/payment | --
|  | - Targeting potentials by location | - Increase "influencers" |  | - Python |  |  |  | 1. What profiles do you want me to analyze ? Yelp , Facebook , instagram etc . Need this from MH .
|  | - Identify competitors |  |  | - R |  |  |  | 2. Competitors - gather list of competitors in DC VA MD region . Ask MH / AH if they want national level data as well .
|  | - Analyze other restaurant content |  |  | - Tableau |  |  |  | 3. What hashtags do you want me to work with . I can start with a few hashtags to begin with , and see what other hashtags are most commonly being used along with them .
[5 empty] | - SD to create code |  |  |  | 4. Targeting by location - search based on what hashtags ?
Things which have not been mentioned : 1. Figure out what kind of images are being posted for each hashtag . 2. Sets of hashtags that work together .
3 | Analyzing Customers | - Identify current guests/clients (who we should market to) | - Data of who our guests vs. clients are | YES | - Interns to collect info. at restaruant (age, gender, etc.) | - SD: 2 weeks for API data | - Hire interns or use machine to do this? (he doesn't say how machine/what tool to use) | - What is his plan for gathering data in social media? I want to see what his requirments are for filtering through or finding our customers | FB, Yelp, INstagram : Scrape people who have reviewed restaurant . Gather data of their profiles .
|  | - Identify guests who are ALSO social media users (help find "influencers") | - Data for new location |  | - Python | - SD: 3 weeks data feature assignment? | - SD asking how catering client data is organized | - He lists several weeks minimum for this task, can he explain? | I have to understand how the API works , then scrape the data from different sources , then combine them into a single place , then decide which attributes to keep and delete , then decide priority of users to target . Takes time .
|  |  | - Data for marketing (ex. new locations, other than bridal shows,) |  | - R | - SD: 1 week for interns at restaurant |  | - Do we provide Base client info? Or can we use WeddingWire as a start/average of what our clients look like? | Info about clients can be classified into two types : client and guest . I will gather guest data from Facebook , yelp , instagram . Client data will have to be provided .
|  |  | - Data current "influencers" who are providing free marketing |  | - Tableau | - SD: 2 weeks to report info |  | - I'd want to see this in a graph of current influencer, guest info, client info
[5 empty] | - Facebook, Instagram, Yelp API |  |  | - Let's start w/ our current restaurnat staff using Google form and tablet using a calendar reminder on the tablet | What ?
Talk to MH about access to google drive menu for catering events .
| Analyzing Menu | - Identify other restaurants (local/national) to determine our menu changes | - Data to create future menu changes | EITHER | - Python | - SD: 2 weeks for gathering info locally | - Provide data on most recent menu change and sales | - Can we run a price menu change analysis on the most recent items added? | Yes .
|  | - Identify our signature dishes |  |  | - Excel | - SD: 3 weeks for gathering info national | - Provide data on previous sales | - It's not necessary now to know some of this info, but it's good to have data rather than going by our gut
|  | - Identify features that correlate with popularity (local/national to see if parking, credit card, etc attribute to popularity) |  |  |  | - SD: 2 weeks to report info |  | - He doesn't talk about how he'd use menu structuring and features that can correlated with popularity, but I don't see this as necessary | Let's say a restaurant X has only appetizers , main , desserts . It has a favorable rating on Yelp . Restaurant Y has appetizers , main course , desserts , sides , drinks and has a less favorable rating on yelp . Can use this to change the structure of menu .
|  | - Identify change in menu affecting sales | [6 empty] | Talk to MH about access to google drive menu for catering events .
3 | Targeting Customers | - Identify currenty guests/clients (who we should market to) | - Data of current "influencers" who are providing free marketing | YES | - Python | - SD: 2 weeks for API data | - SD asking how to store data (possibly Google Spreadsheet?) | - I'd want to see this in a graph of current influencer, guest info, client info (same note as earlier task) | Will need client data .
|  | - Identify guests/clients who are ALSO social media users (help find "influencers") | - Establish a relationship w/ "influencers" |  | - Excel | - SD: 1.5 weeks for collecting data |  | - This task can be done simultaneously with analysing guests and clients | Yes .
|  | - Create requirments for future guests/clients (who we want to market to) | - Reach potential guests/clients |  | - Gephi | - SD: 2 weeks for calculating
[5 empty] | - SD to create code | - SD: 2 weeks to report info
- SD compile all data
- Complete analyzing guests and clients task first
| Blog Content | - Identify active food blogs | - Data of blog info, keywords, frequency | EITHER | - Python | - SD: ongoing task |  | - Is a blog necessary? | Not really . Either run an active blog or don't at all .
|  |  | - Create similar blogs based on data |  | - Excel | - SD: 4 weeks for data of restaurants w/ active blogs |  | - How will this generate money? OR is this blog writting a task to give an intern? | Not going to generate money based on the blog posts on the indaroma blog posts as such . The idea is to find other blogs which are willing to take guest posts , so you can reach their audience . Also helps with SEO . | Additionally, helps identify keywords to put into the guest post , SEO keywords to use in website , content details for guest posts .
|  |  | - Use keywords to optimize website |  | - Tableau | - SD: 3 weeks to analyse data |  | - We should consider analysing travel video blogs, trending on Facebook: https://www.buzzfeed.com/bringme | How ? What do I have to do here ?
[5 empty] | - Purchase allowed API ($5) | - SD/MH: 2 hrs to establish requirments of search |  |  | Talk to MH about gathering list of food blogs , blogger for content via fiverr .
| Website Tracking | Heatmap for website - we don't need this now |  | NO |  |  |  | Crazyegg ?
| Not mentioned | Website changes backend
Facebook bot
weddingwire ... not easy to gather data . Talk about what else can be gathered from the site .