## Sheet1
Priority | Task | Task Details | Goal | Necessary | Resources Needed | Time Allocated | Follow-Up Needed (AH) | Notes
1 | Post to Social Media | - Establish a frequency of posts | - Marketing strategy | YES | - Hootsuite credentials | - SD: 1 day | - Change Hootsuite credentials | --
|  | - Create requirements (ex. 4 PM daily) | - Consistant posts |  | - MH create requirments | - MH: 2 hour (create info and teach SD)
- Establish social medias
| Automate Instagram | - Autolikeing | -Social media popularity | EITHER | - Instagram credentials |  | - Change Instagram credentials | - Can we use bots for Facebook? Or Twitter?
|  | - Autocommenting | - Increase "influencers" |  | - Setup test profile | - SD: 1 week (30 hrs) |  | - We're don't have a lot of people commenting/talking to us on social media, but we should get into trend of "liking" posts to increase our followers
[5 empty] | - Purchase bots..$7-20 (robolike, gramista, instazood) |  |  | - Will the bots also help us find people to follow in social media? This could increase our followers in return (ex. you scratch my back)
2 | Analyzing Other Profiles | - Researching hashtags | - Social media popularity | YES | - Instagram credentials | - SD/MH: ongoing task | - SD asking how many hours are allowed/payment | --
|  | - Targeting potentials by location | - Increase "influencers" |  | - Python
|  | - Identify competitors |  |  | - R
|  | - Analyze other restaurant content |  |  | - Tableau
- SD to create code
3 | Analyzing Customers | - Identify current guests/clients (who we should market to) | - Data of who our guests vs. clients are | YES | - Interns to collect info. at restaruant (age, gender, etc.) | - SD: 2 weeks for API data | - Hire interns or use machine to do this? (he doesn't say how machine/what tool to use) | - What is his plan for gathering data in social media? I want to see what his requirments are for filtering through or finding our customers
|  | - Identify guests who are ALSO social media users (help find "influencers") | - Data for new location |  | - Python | - SD: 3 weeks data feature assignment? | - SD asking how catering client data is organized | - He lists several weeks minimum for this task, can he explain?
|  |  | - Data for marketing (ex. new locations, other than bridal shows,) |  | - R | - SD: 1 week for interns at restaurant |  | - Do we provide Base client info? Or can we use WeddingWire as a start/average of what our clients look like?
|  |  | - Data current "influencers" who are providing free marketing |  | - Tableau | - SD: 2 weeks to report info |  | - I'd want to see this in a graph of current influencer, guest info, client info
[5 empty] | - Facebook, Instagram, Yelp API |  |  | - Let's start w/ our current restaurnat staff using Google form and tablet using a calendar reminder on the tablet
| Analyzing Menu | - Identify other restaurants (local/national) to determine our menu changes | - Data to create future menu changes | EITHER | - Python | - SD: 2 weeks for gathering info locally | - Provide data on most recent menu change and sales | - Can we run a price menu change analysis on the most recent items added?
|  | - Identify our signature dishes |  |  | - Excel | - SD: 3 weeks for gathering info national | - Provide data on previous sales | - It's not necessary now to know some of this info, but it's good to have data rather than going by our gut
|  | - Identify features that correlate with popularity (local/national to see if parking, credit card, etc attribute to popularity) |  |  |  | - SD: 2 weeks to report info |  | - He doesn't talk about how he'd use menu structuring and features that can correlated with popularity, but I don't see this as necessary
- Identify change in menu affecting sales
3 | Targeting Customers | - Identify currenty guests/clients (who we should market to) | - Data of current "influencers" who are providing free marketing | YES | - Python | - SD: 2 weeks for API data | - SD asking how to store data (possibly Google Spreadsheet?) | - I'd want to see this in a graph of current influencer, guest info, client info (same note as earlier task)
|  | - Identify guests/clients who are ALSO social media users (help find "influencers") | - Establish a relationship w/ "influencers" |  | - Excel | - SD: 1.5 weeks for collecting data |  | - This task can be done simultaneously with analysing guests and clients
|  | - Create requirments for future guests/clients (who we want to market to) | - Reach potential guests/clients |  | - Gephi | - SD: 2 weeks for calculating
[5 empty] | - SD to create code | - SD: 2 weeks to report info
- SD compile all data
- Complete analyzing guests and clients task first
| Blog Content | - Identify active food blogs | - Data of blog info, keywords, frequency | EITHER | - Python | - SD: ongoing task |  | - Is a blog necessary?
|  |  | - Create similar blogs based on data |  | - Excel | - SD: 4 weeks for data of restaurants w/ active blogs |  | - How will this generate money? OR is this blog writting a task to give an intern?
|  |  | - Use keywords to optimize website |  | - Tableau | - SD: 3 weeks to analyse data |  | - We should consider analysing travel video blogs, trending on Facebook: https://www.buzzfeed.com/bringme
[5 empty] | - Purchase allowed API ($5) | - SD/MH: 2 hrs to establish requirments of search
| Website Tracking | Heatmap for website - we don't need this now |  | NO

## Sheet2
Questions for Form
Time of day | Automatic
Estimated age
# of people
Gender
Estimated revenue